## Sheet1
Week Number
Task |  | 4 | 5 | 6 | 7 | 5 | 9 | 10 | 11 | 12
Decide on project | bar: Week Number 4
Prepare project proposal | bar: Week Number 4 to Week Number 5
Obtain RGB-D Cameras | bar: Week Number 5 to Week Number 6
Configure development environment | bar: Week Number 5 to Week Number 7
Prototype algorithms | bar: Week Number 5 to Week Number 7
Generate pseudocode | bar: Week Number 7
Write mid-review report | bar: Week Number 6 to Week Number 7
Write software | bar: Week Number 7 to Week Number 10
Edit video | bar: Week Number 9 to Week Number 10
Write report | bar: Week Number 10 to Week Number 12
Prepare presentation | bar: Week Number 11 to Week Number 12
Deliverables
Project proposal | bar: Week Number 5
Mid-review report | bar: Week Number 7
Code submission | bar: Week Number 10
Video | bar: Week Number 10
Teaser presentation | bar: Week Number 12
Final Report | bar: Week Number 12